## Data
Action Plan Template - Project Name
Supervisor Name |  | John Smith
Start Date |  | 2023-05-01 |  | End Date | 2023-06-30
Activity | Start Date | End Date | Assigned to | Priority | Status | Observations
Activity #1 | 2023-05-01 | 2023-05-31 | Employee #1 | High | 10%
Task #1 | 2023-05-01 | 2023-05-15 | Employee #2 | Medium | 25%
Task #2 | 2023-05-15 | 2023-05-20 | Employee #2 | Medium | Not started
Task #3 | 2023-05-01 | 2023-05-31 | Employee #3 | Low | 10%
Task #4 | 2023-05-15 | 2023-05-31 | Employee #3 | Low | Not started
Activity #2 | 2023-06-01 | 2023-06-30 | Employee #4 | High | Not started
Task #1 | 2023-06-01 | 2023-06-15 | Employee #5 | Low | Not started
Task #2 | 2023-06-01 | 2023-06-10 | Employee #6 | High | Not started
Task #3 | 2023-06-15 | 2023-06-30 | Employee #8 | Medium | Not started
Task #4 | 2023-06-15 | 2023-06-30 | Employee #9 | Medium | Not started

## Legend
Activity | Employees | Priority | Status
Activity #1 | Employee #1 | Low | Not started
Task #1 | Employee #2 | Medium | 10%
Task #2 | Employee #3 | High | 25%
Task #3 | Employee #4 |  | 50%
Task #4 | Employee #5 |  | 75%
Activity #2 | Employee #6 |  | Done
Task #1 | Employee #7
Task #2 | Employee #8
Task #3 | Employee #9
Task #4
Activity #3
Task #1
Task #2
Task #3
Task #4
Activity #4
Task #1
Task #2
Task #3